## Slide 1: Object based estimation technique
BITS Pilani
Viswanathan Hariharan
2015

## Slide 2: Object based estimation
This is a flexible estimation approach that can be adapted to different types of projects
For example, some projects have screens & reports as objects. Others have configurations settings as objects (ex, ERP package implementation), others have change requests as objects
This technique determines the size of project based on number of objects and their complexity
Please note that this is not the same as Object Point technique

## Slide 3: Object based estimation
Steps:
  List all objects of different categories
  Assign points to each object based on its complexity (Low, Medium, High)
  Determine the total points
  Finally convert the Points to effort based on Calibrated Historical data
Note: The classification of objects and the way to determine their complexity needs to be done by each organization depending on the nature of projects executed

## Slide 4: Assigning points, based on complexity of objects: Example
Point based on complexity
Object type | Complexity -> | Low | Medium | High
Screen |  | 2 | 4 | 8
Report |  | 1 | 2 | 3
Interface |  | 2 | 4 | 8
Points will differ from organization to organization. It has to be based on historical data of effort needed to develop & test these objects

## Slide 5: Object based estimation: Example
Screens | Name of screen | Complexity | Points
 | Account maintenance | High | 8
 | Funds transfer | Medium | 4
 | Pay bills | Low | 2
Reports | Name of report | Complexity | Points
 | Generate monthly statement | High | 3
 | Print last 10 transactions | Medium | 2
Interfaces | Name of interface | Complexity | Points
 | Send statement via email | Low | 2
 | Receive government rules | Medium | 4
Total Object points |  |  | 25

## Slide 6
Given below are some parameters that can be used to determine complexity of objects:
  Screen complexity: can be determined based on number of fields on the screen, number of command buttons,
  Report complexity: can be determined based on number of fields in the report, number of data files needed
  Interface complexity: can be determined by the number of data items sent or received, number of data files needed
Parameters that determine complexity of objects: Example

## Slide 7
Screen complexity determination: Example
 |  | Number of fields
 |  | <5 | 6 - 10 | > 10
Number of command buttons | 1 | Simple | Simple | Medium
2 - 3 | Simple | Medium | Medium
> 3 | Simple | Complex | Complex
Determining complexity of objects: Example

## Slide 8
Object based estimation is a flexible approach that can be adapted to different types of projects
Projects need to identify suitable types of objects based on the type of project
The size of projects are estimated based on number of objects and complexity of objects
Summary