## Slide 1: Planning for different phases of a project
BITS Pilani
Viswanathan Hariharan
2015

## Slide 2: Estimating effort for different phases
Once the size of the project is estimated using FPs or Object points, we can convert the size into effort, based on calibrated historical data
We can then distribute the total effort across different phases of the project, again based on historical data
For example:
  7% for Requirement gathering
  8% for Requirement analysis
  20% for architecture & design
  45% for construction
  15% for System testing
  5% for Project management

## Slide 3: Estimating effort: Other considerations
There may be other factors to consider:
  Configuration management: 2-5% of technical effort
  Requirement change: 1-4% effort per elapse month
  First time development with new language & tool: 20- 40% effort
  Contingency depending on risk severity & probability: 5-10%
Note: All percentages are illustrative only. Actual percentages should be based on historical data

## Slide 4: Use of multiple approaches
In case of large projects, we should not depend on one approach to estimation, because there could be some aspects which might have been overlooked
Hence it is recommended to use multiple estimation techniques and compare the results
If the difference is large then it is likely that some aspects have been overlooked
We should try to understand the reason for the difference
Then we should re-estimate until results converge to within 10%

## Slide 5: Estimation negotiation techniques
Project managers encounter situations where stakeholders ask for changes to estimation. Here are some ways to handle them:
If Marketing team tells you to reduce the cost or effort
  Use historical data to justify the effort calculations
If more features are requested without adding more effort
  Move some functions to version 2, or
  Cut features altogether, if the business value is low
When you are asked to complete the project faster
  Ask for more developers & testers & team leads, or
  Add higher skilled technical staff, or
  Ask what features are a ‘must have’ & what are not required